## Blank
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost optimization
Φ
Φ
Φ
CI-CD Setup For Firestorm
Φ
B. | Inprogress Items
CI-CD Setup For Firestorm
Φ
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 14th March 2025 | Holi
B. | Team Members Leaves
| Φ | NA

## 10-13 Mar 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost optimization
| Φ | FIRPRO-6 | Platinum feature analysis
| Φ | FIRPRO-14 | Identify Alternative Solutions to Elasticsearch
| Φ | FIRPRO-21 | Analyse and explore Apache Solr
CI-CD Setup For Firestorm
| Φ | FIRPRO-28 | Documentation for Petar about CI/CD plan
B. | Inprogress Items
CI-CD Setup For Firestorm
| Φ | FIRPRO-23 | Create a job yml file for Github Actions CI/CD | We are working on to create a job.yml file along with building app, logstash and UI components.
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 14th March 2025 | Holi
B. | Team Members Leaves
| Φ | NA

## 17-21 Mar 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost optimization
| Φ | FIRPRO-34 | Analyse Apache NiFi to replicate CCR
| Φ | FIRPRO-32 | Perform POC of using Spark job as Kafka Consumer
B. | Inprogress Items
Elastic Cost optimization
| Φ | FIRPRO-33 | Analyse Java application code changes to replicate CCR | We have completed the code changes and currently testing them
| Φ | FIRPRO-35 | Analyse Logstash changes to replicate CCR | We are currently doing config changes
CI-CD Setup For Firestorm
| Φ | FIRPRO-23 | Create a job yml file for Github Actions CI/CD | We have completed the build pipeline and currently working on deploy pipeline
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 14th March 2025 | Holi
| Φ | 31st March 2025 | Ramzan (Idu'I Fitr)
B. | Team Members Leaves
| Φ | NA

## 24-28 Mar 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost optimization
| Φ | FIRPRO-33 | Analyse Java application code changes to replicate CCR
| Φ | FIRPRO-35 | Analyse Logstash changes to replicate CCR
| Φ | FIRPRO-39 | Create Locust setup for API driven load testing
CI-CD Setup For Firestorm
| Φ | FIRPRO-23 | Create a job yml file for Github Actions CI/CD
B. | Inprogress Items
Elastic Cost optimization
| Φ | FIRPRO-37 | Perform integration testing on Local Lab with updated changes | Team is currently testing API and Kafka event based functional scenarios.
| Φ | FIRPRO-38 | Elasticsearch version downgrade roll-out and rollback steps | Team is preparing roll-out and roll-back doc.
| Φ | FIRPRO-40 | Create Kafka producer setup for performing Kafka event driven load testing | Team is working on creating Kafka event stimulator for planned load testing.
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 14th March 2025 | Holi
B. | Team Members Leaves
| Φ | NA

## 31 Mar - 4 Apr 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost optimization
| Φ | FIRPRO-41 | Perform Baseline testing on Local Lab
| Φ | FIRPRO-42 | Perform load testing on Local Lab
| Φ | FIRPRO-43 | Perform dry run of roll-out and rollback steps on Local Lab
B. | Inprogress Items
Elastic Cost optimization
| Φ | FIRPRO-40 | Create Kafka producer setup for performing Kafka event driven load testing | Team is currently testing this kafka producer utility
| Φ | FIRPRO-44 | Create test suite for ESPersistanceManger to test the changes in DR | Team is writing test suite for ESPersistanceManger
CI-CD Setup For Firestorm
| Φ | FIRPRO-36 | Setup a new AWS instance for FIrestorm Pro | Team has completed the installation part and currently working on bringing up the services
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 18th April 2025 | Good Friday
B. | Team Members Leaves
| Φ | 2nd, 3rd, 4th April 2025 | Shilratna Somkuwar
| Φ | 1st April 2025 | Shruthi Joshi

## 7 Apr - 11 Apr 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost optimization
| Φ | FIRPRO-45 | Deploy ES downgrade changes to BT UAT environment
CI-CD Setup For Firestorm
| Φ | FIRPRO-36 | Setup a new AWS instance for FIrestorm Pro
B. | Inprogress Items
Elastic Cost optimization
| Φ | FIRPRO-46 | Add conditional Elasticsearch DR update in logstash pipeline | Team is currently testing these changes on Local Lab
| Φ | FIRPRO-47 | Analyse Keycloak and its usage | Team is currently analysing Keycloak
| Φ | FIRPRO-48 | Analyse changes needed for ES DR switchover | Team has identified the changes needed for actual switchover
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 18th April 2025 | Good Friday
B. | Team Members Leaves
| Φ | 7th April 2025 | Shilratna Somkuwar

## 14 Apr - 18 Apr 2025
Risk
A. | Φ | There is a lack of cooperation from BT and its stakeholders to initiate E2E testing for the Elasticsearch changes. We require assistance from Graham to escalate this to BT management.
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost Optimization
| Φ | FIRPRO-48 | Analyse changes needed for ES DR switchover
Keycloak Integration
| Φ | FIRPRO-47 | Analyse Keycloak and its usage
B. | InProgress Items
Elastic Cost Optimization
| Φ | FIRPRO-46 | Add conditional Elasticsearch DR update in logstash pipeline | Team is currently testing these changes on Local Lab
| Φ | FIRPRO-49 | Develop automated monitoring scripts | Team is currently writing these scripts
| Φ | FIRPRO-50 | Develop automated Prod roll-out scripts | Team is currently writing these scripts
Keycloak Integration
| Φ | FIRPRO-52 | Perform POC around Keycloak | Team is currently testing the local Keycloak setup
CI-CD Setup For Firestorm
| Φ | FIRPRO-51 | Setup CI/CD pipeline on new AWS instance | Team is currently working on setting-up pipeline
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 18th April 2025 | Good Friday
B. | Team Members Leaves
| Φ | NA

## 21 Apr - 25 Apr 2025
Risk
Φ | NA
Highlights
Team successfully downgraded the Elasticsearch platinum license to basic on BT Production environment. This strategic move will unlock significant annual cost savings for Resolve, estimated at approximately $170K!
Project Summary Details
A. | Completed Items
Elastic Cost Optimization
| Φ | FIRPRO-49 | Develop automated monitoring scripts
| Φ | FIRPRO-50 | Develop automated Prod roll-out scripts
| Φ | FIRPRO-53 | Deployment of ES downgrade changes on BT Production environment
Keycloak Integration
| Φ | FIRPRO-52 | Perform POC around Keycloak
B. | InProgress Items
Elastic Cost Optimization
| Φ | FIRPRO-46 | Add conditional Elasticsearch DR update in logstash pipeline | Team is currently testing these changes on Local Lab
CI-CD Setup For Firestorm
| Φ | FIRPRO-51 | Setup CI/CD pipeline on new AWS instance | Team is currently working on setting-up pipeline
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 18th April 2025 | Good Friday
B. | Team Members Leaves
| Φ | 24th, 25th April 2025 | Shruthi Joshi

## 28 Apr - 2 May 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost Optimization
| Φ | FIRPRO-46 | Add conditional Elasticsearch DR update in logstash pipeline
B. | InProgress Items
Elastic Cost Optimization
| Φ | FIRPRO-64 | Test DR Switchover scenario on Local Lab | Team is currently testing changes on Local Lab
CI-CD Setup For Firestorm
| Φ | FIRPRO-51 | Setup CI/CD pipeline on new AWS instance | Team is currently working on setting-up CD pipeline
Keycloak Integration
| Φ | FIRPRO-57 | BE: Keycloak JWT Authentication Setup | Team is currently working on code changes
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 1st May 2025 | May Day
B. | Team Members Leaves
| Φ | 2nd May 2025 | Shilratna Somkuwar

## 5 May - 9 May 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost Optimization
| Φ | FIRPRO-64 | Test DR Switchover scenario on Local Lab
B. | InProgress Items
Elastic Cost Optimization
| Φ | FIRPRO-68 | Create DR Switchover Deployment Plan | Team is currently creating deployment plan
CI-CD Setup For Firestorm
| Φ | FIRPRO-51 | Setup CI/CD pipeline on new AWS instance | Pipeline is working on forked project. Team is now replicating the same on firestorm project
Keycloak Integration
| Φ | FIRPRO-57 | BE: Keycloak JWT Authentication Setup | Team is currently testing the changes
| Φ | FIRPRO-58 | BE: Tenant-Aware Issuer Resolution and Token Decoding | Team is currently testing the changes
QA Wolf Enablement
| Φ | FIRPRO-66 | Analyse system readiness for QA wolf handover | Team is currently working on getting system ready for handover
| Φ | FIRPRO-70 | Identify existing UI issues | Team has listed down open UI issues
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 1st May 2025 | May Day
B. | Team Members Leaves
| Φ | NA

## 12 May - 16 May 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Cost Optimization
| Φ | FIRPRO-69 | Perform load testing for DR switchover
Keycloak Integration
| Φ | FIRPRO-57 | BE: Keycloak JWT Authentication Setup
| Φ | FIRPRO-58 | BE: Tenant-Aware Issuer Resolution and Token Decoding
QA Wolf Enablement
| Φ | FIRPRO-70 | Identify existing UI issues
B. | InProgress Items
Elastic Cost Optimization
| Φ | FIRPRO-68 | Create DR Switchover Deployment Plan | Team is currently creating deployment plan
Keycloak Integration
| Φ | FIRPRO-59 | BE: Token Expiry & Access Control Handling | Team is working on code changes
QA Wolf Enablement
| Φ | FIRPRO-66 | Analyse system readiness for QA wolf handover | Team is currently working on getting system ready for handover
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is working on setting up Mockoon server
| Φ | FIRPRO-74 | Analyse BE API calls for each UI frame | Team is documenting BE API calls for UI frames
CI-CD Setup For Firestorm
| Φ | FIRPRO-51 | Setup CI/CD pipeline on new AWS instance | Team is testing CI/CD setup over deployment branch
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 1st May 2025 | May Day
B. | Team Members Leaves
| Φ | 15th May 2025 | Saurabha Patane

## 19 May - 23 May 2025
Risk
Φ | NA
Highlights
The engagement with QA Wolf commenced with a successful kick-off call, laying the groundwork for effective future collaboration.
Project Summary Details
A. | Completed Items
Elastic Search Enhancements
| Φ | FIRPRO-68 | Create DR Switchover Deployment Plan
Keycloak Integration
| Φ | FIRPRO-59 | BE: Token Expiry & Access Control Handling
| Φ | FIRPRO-75 | Ensure the application works with default realm structure
QA Wolf Enablement
| Φ | FIRPRO-66 | Analyse system readiness for QA wolf handover
CI-CD Setup For Firestorm
| Φ | FIRPRO-51 | Setup CI/CD pipeline on new AWS instance
B. | InProgress Items
Elastic Search Enhancements
| Φ | FIRPRO-79 | Prepare the build of DR switchover for BT's T3 testing | Team is currently testing the build on local lab
Keycloak Integration
| Φ | FIRPRO-60 | BE: Configuration, Testing, and Docs | Team is documenting the Keycloak details
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is working on creating mock API's for priority UI frames
| Φ | FIRPRO-74 | Analyse BE API calls for each UI frame | Team is documenting BE API calls for priority UI frames
| Φ | FIRPRO-77 | Setup Mockoon server on AWS dev instance | Team is working on setting up CLI based server on AWS dev instance
CI-CD Setup For Firestorm
| Φ | FIRPRO-76 | CI/CD setup for fs-core repository | Team is working on creating CI/CD setup for fs-core repo similar to firestorm repo
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 1st May 2025 | May Day
B. | Team Members Leaves
| Φ | NA

## 26 May - 30 May 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Search Enhancements
| Φ | FIRPRO-79 | Prepare the build of DR switchover for BT's T3 testing
QA Wolf Enablement
| Φ | FIRPRO-74 | Analyse BE API calls for each UI frame
| Φ | FIRPRO-77 | Setup Mockoon server on AWS dev instance
B. | InProgress Items
Keycloak Integration
| Φ | FIRPRO-60 | BE: Configuration, Testing, and Docs | Team is currently writing test cases
| Φ | FIRPRO-61 | UI: Keycloak Front-End Integration | Team is currently testing the changes locally
| Φ | FIRPRO-62 | UI: JWT Token Handling & Route Protection | Code changes are in-progress
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is working on creating mock API's for priority UI frames
CI-CD Setup For Firestorm
| Φ | FIRPRO-76 | CI/CD setup for fs-core repository | Team is working on creating CI/CD setup for fs-core repo similar to firestorm repo
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 1st May 2025 | May Day
B. | Team Members Leaves
| Φ | 29th, 30th May 2025 | Saurabha Patane

## 2 June - 6 June 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Keycloak Integration
| Φ | FIRPRO-60 | BE: Configuration, Testing, and Docs
| Φ | FIRPRO-61 | UI: Keycloak Front-End Integration
CI-CD Setup For Firestorm
| Φ | FIRPRO-76 | CI/CD setup for fs-core repository
B. | InProgress Items
Keycloak Integration
| Φ | FIRPRO-62 | UI: JWT Token Handling & Route Protection | Code changes are in-progress
| Φ | FIRPRO-84 | BE: Keyclock setup on AWS instance | Team is working on setting up Keycloak on DEV AWS instance
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is testing mock API's for priority UI frames locally
| Φ | FIRPRO-86 | Analyse UI User workflows shared by QA Wolf | Analysis is in-progress
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 5th (half day), 6th June 2025 | Smita Chougule

## 9 June - 13 June 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
QA Wolf Enablement
| Φ | FIRPRO-86 | Analyse UI User workflows shared by QA Wolf
CI-CD Setup For Firestorm
| Φ | FIRPRO-90 | Setup new build jar files of fs-core to firestorm dev instance
B. | InProgress Items
Keycloak Integration
| Φ | FIRPRO-62 | UI: JWT Token Handling & Route Protection | Testing is in-progress
| Φ | FIRPRO-63 | UI: Token Expiry Management & UX Shell | Testing is in-progress
| Φ | FIRPRO-84 | BE: Keyclock setup on AWS instance | Team is working on setting up Keycloak on DEV AWS instance
| Φ | FIRPRO-91 | Open keyclock API to public IP | Team is currently working on to expose public IP
| Φ | FIRPRO-92 | BE: Keycloak setup on test env (local lab) | Setup is in-progress
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is testing mock API's for priority UI frames locally
CI-CD Setup For Firestorm
| Φ | FIRPRO-67 | Enable ELK on new AWS instance | Changes are in-progress
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 9th,13th June 2025 | Shilratna Somkuwar
| Φ | 9th (half day) June 2025 | Shruthi Joshi

## 16 June - 20 June 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Keycloak Integration
| Φ | FIRPRO-84 | BE: Keyclock setup on AWS instance
| Φ | FIRPRO-92 | BE: Keycloak setup on Resolve test env (local lab)
| Φ | FIRPRO-91 | Open keyclock API to public IP
CI-CD Setup For Firestorm
| Φ | FIRPRO-67 | Enable ELK on new AWS instance
B. | InProgress Items
Keycloak Integration
| Φ | FIRPRO-62 | UI: JWT Token Handling & Route Protection | Testing is in-progress
| Φ | FIRPRO-63 | UI: Token Expiry Management & UX Shell | Testing is in-progress
| Φ | FIRPRO-81 | UI: Test Integration | Testing is in-progress
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is testing mock API's for priority UI frames locally
CI-CD Setup For Firestorm
| Φ | FIRPRO-93 | Add AWS Dev Firestorm Pro instance to monitoring | Changes are in-progress
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | NA

## 23 June - 27 June 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Keycloak Integration
| Φ | FIRPRO-62 | UI: JWT Token Handling & Route Protection
| Φ | FIRPRO-63 | UI: Token Expiry Management & UX Shell
B. | InProgress Items
Keycloak Integration
| Φ | FIRPRO-81 | UI: Test Integration | Testing is in-progress
| Φ | FIRPRO-80 | UI: Role & Realm-based Access Control | Changes are in-progress
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is setting up mock API's on DEV AWS instance
CI-CD Setup For Firestorm
| Φ | FIRPRO-93 | Add AWS Dev Firestorm Pro instance to monitoring | Changes are in-progress
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 25th (half day) June 2025 | Shruthi Joshi
| Φ | 26th June 2025 | Shilratna Somkuwar

## 30 June - 4 July 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Keycloak Integration
| Φ | FIRPRO-81 | UI: Test Integration
CI-CD Setup For Firestorm
| Φ | FIRPRO-94 | Fix CI/CD broken pipeline
| Φ | FIRPRO-95 | Open Mockoon accessibility on https
B. | InProgress Items
Keycloak Integration
| Φ | FIRPRO-80 | UI: Role & Realm-based Access Control | Analysis is in-progress
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is integrating mock API's on DEV AWS instance
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 30th June 2025 | Saurabha Patane

## 7 July - 11 July 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
QA Wolf Enablement
| Φ | FIRPRO-98 | Analyse QA Wolf issue: Incidents tab showing 500 errors
| Φ | FIRPRO-99 | Analyse QA Wolf issue: Site health only displaying 1 page, first 10 items
| Φ | FIRPRO-100 | Analyse QA Wolf issue: Top Affected Site in red, device displays green
B. | InProgress Items
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team has deployed all the priority UI frames on AWS Dev instance
CI-CD Setup For Firestorm
| Φ | FIRPRO-96 | Integrate CI-CD and QA-Wolf | Pipeline changes are in-progress
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 7th, 8th July 2025 | Chandrakhan Dudekula
| Φ | 11th July 2025 | Smita Chougule

## 14 July - 18 July 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
CI-CD Setup For Firestorm
| Φ | FIRPRO-96 | Integrate CI-CD and QA-Wolf
B. | InProgress Items
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is analysing reported open issues
CI-CD Setup For Firestorm
| Φ | FIRPRO-93 | Add AWS Dev Firestorm Pro instance to monitoring | Team is working on creating dashboard for firedev server on Zabbix
Elastic Search Enhancements
| Φ | FIRPRO-65 | Add anomaly detection (external) with Elastic Search Basic version | Analysis in in-progress
CSS Overhaul to Resolve Style
| Φ | FIRPRO-87 | Design Audit: Compare current styles with the Resolve style guidelines to identify required changes. | Analysis in in-progress
UI - AngularJs Upgrade
| Φ | FIRPRO-106 | Feasibility check to upgrade the AngularJS with latest angular version | Analysis in in-progress
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 18th July 2025 | Shruthi Joshi

## 21 July - 25 July 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
Elastic Search Enhancements
| Φ | FIRPRO-65 | Add anomaly detection (external) with Elastic Search Basic version
CI-CD Setup For Firestorm
| Φ | FIRPRO-93 | Add AWS Dev Firestorm Pro instance to monitoring
UI - AngularJs Upgrade
| Φ | FIRPRO-106 | Feasibility check to upgrade the AngularJS with latest angular version
B. | InProgress Items
Elastic Search Enhancements
| Φ | FIRPRO-109 | Perform POC around Anomaly detection | Basic POC is completed. Team is expanding it further
QA Wolf Enablement
| Φ | FIRPRO-73 | Generate Reliable Test Data Using Mockoon for QA Automation | Team is analysing reported open issues
CI-CD Setup For Firestorm
| Φ | FIRPRO-107 | Analyze if multiple instances of application can run on our AWS dev instance | Analysis is in-progress
CSS Overhaul to Resolve Style
| Φ | FIRPRO-87 | Design Audit: Compare current styles with the Resolve style guidelines to identify required changes. | Team is analysing current CSS styles with Resolve guidelines
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 21st July 2025 | Chandrakhan Dudekula
| Φ | 21st July 2025 | Shruthi Joshi
| Φ | 22nd, 23rd, 24th, 25th July 2025 | Shilratna Somkuwar

## 04 Aug - 08 Aug 2025
Risk
Φ | NA
Highlights
Φ | Nikhil Naik took over from Shruthi Joshi effective 11th August 2025
Project Summary Details
A. | Completed Items
Elastic Search Enhancements
| Φ | FIRPRO-109 | Perform POC around Anomaly detection | Pausing these efforts due to prioritization of Firestorm-Pro and Insights merge efforts
B. | InProgress Items
CI-CD Setup For Firestorm
| Φ | FIRPRO-124 | Configure new AWS dev instance and install Firestorm Pro | Team continued to work on new AWS instance configuration
CSS Overhaul to Resolve Style
| Φ | FIRPRO-123 | Style Refactoring: Update or rewrite the CSS/SCSS code to meet the new design standards. | Code changes and testing on local system is completed. Code review is in-progress followed by deployement on dev instance
QA Wolf Regression Issues/Bugs
| Φ | FIRPRO-125 | [Regression] Site health for healthy site not displaying correct amount | Analysis is in-progress, however, substantial updates to the mock API are required, so it’s currently paused
Merge Firestorm Pro with Insights
| Φ | FIRPRO-129 | Explore current firestorm pro codebase in backend | Currently analyzing the Insights product documentation and investigating BFG flow for device document creation
| Φ | FIRPRO-130 | Explore current firestorm pro codebase and find out libraries used and its version dependency | Made a note of exisiting libraries and its versions Investigating backend for UI Rendering to be compared with Insights
| Φ | FIRPRO-132 | Compare UI features of Insights and Firestorm PRO | Listed down the APIs with description, invstigating and updating connector details
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 15th August 2025 | Independence Day
| Φ | 26th August 2025 | Vinayak Chathurthi
B. | Team Members Leaves
| Φ | 4th August 2025 | Shilratna Somkuwar
| Φ | 5th August 2025 | Jairam Gauns

## 11 Aug - 15 Aug 2025
Risk
Φ | NA
Highlights
Φ
Project Summary Details
A. | Completed Items
Elastic Search Enhancements
| Φ | FIRPRO-109 | Perform POC around Anomaly detection | Pausing these efforts due to prioritization of Firestorm-Pro and Insights merge efforts
B. | InProgress Items
CI-CD Setup For Firestorm
| Φ | FIRPRO-124 | Configure new AWS dev instance and install Firestorm Pro | Team continued to work on new AWS instance configuration
CSS Overhaul to Resolve Style
| Φ | FIRPRO-123 | Style Refactoring: Update or rewrite the CSS/SCSS code to meet the new design standards. | Code changes and testing on local system is completed. Code review is in-progress followed by deployement on dev instance
QA Wolf Regression Issues/Bugs
| Φ | FIRPRO-125 | [Regression] Site health for healthy site not displaying correct amount | Analysis is in-progress, however, substantial updates to the mock API are required, so it’s currently paused
Merge Firestorm Pro with Insights
| Φ | FIRPRO-129 | Explore current firestorm pro codebase in backend | Currently analyzing the Insights product documentation and investigating BFG flow for device document creation
| Φ | FIRPRO-130 | Explore current firestorm pro codebase and find out libraries used and its version dependency | Made a note of exisiting libraries and its versions Investigating backend for UI Rendering to be compared with Insights
| Φ | FIRPRO-132 | Compare UI features of Insights and Firestorm PRO | Listed down the APIs with description, invstigating and updating connector details
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 15th August 2025 | Independence Day
| Φ | 26th August 2025 | Vinayak Chathurthi
B. | Team Members Leaves
| Φ | 4th August 2025 | Shilratna Somkuwar
| Φ | 5th August 2025 | Jairam Gauns

## 01 Sept - 05 Sept 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
| Φ | NA
B. | InProgress Items
Merge Firestorm Pro with Insights
| Φ | INS-1182 | Understand the insight installation | Comparing chef cookbooks and firestorm ansible to identify configuration for common and different service to understand
| Φ | INS-1183 | Compare UI features of Insights and Firestorm PRO | Exploring UI libraries and going through insights codebase
| Φ | INS-1185 | Explore Indices Unification Feasibility wrt Device topology | Exploring and comparing indices for devices to decide canonical index
| Φ | INS-1186 | Indices Unification on org, site, users | Exploring and comparing indices for organization, sites, users to decide canonical index
C. | Blocked Items
CI/CD setup for Firestorm
| Φ | FIRPRO-124 | Configure new AWS dev instance and install Firestorm Pro | Task on hold, priority on task INS-1182
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 1st Sept 2025 | Jairam Gauns
| Φ | 1st, 2nd Sept 2025 | Saurabha Patane
| Φ | 1st, 2nd Sept 2025 | Sonal Yewale
| Φ | 1st Sept 2025 | Smita Chougule

## 08 Sept - 12 Sept 2025
Risk
Φ | NA
Highlights
Φ | Code base decision was finalized and Insights would be used as the base product. The current invetigation/development will be aligned to move feature gradually intp codebase
Project Summary Details
A. | Completed Items
| Φ | NA
B. | InProgress Items
Product merge - Tech investigation
| Φ | INS-1182 | Understand the insight installation | Investigate on rabbitmq related cookbooks and configuration
| Φ | INS-1194 | Integrate Logstash | Working on sub ticket INS-1207
| Φ | INS-1207 | Analysis of the Snow Connector in the Firestorm-Pro Logstash Codebase | Checking the flow considering SNOW connector
| Φ | INS-1205 | UI: New Insights-UI Code Base Exploration and Setup | Local setup of insights and component exploration wrt Event Center screen
[Events] Event Center Merge
| Φ | INS-1201 | Implement Event propagation layer | Working on understanding the Rabbitmq publisher mechanism and migrate to insights
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | NA

## 15 Sept - 19 Sept 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
[Events] Event Center Merge
| Φ | INS-1201 | Implement Event propagation layer
Product merge - Tech investigation
| Φ | INS-1194 | Integrate Logstash
| Φ | INS-1207 | Analysis of the Snow Connector in the Firestorm-Pro Logstash Codebase
| Φ | INS-1205 | UI: New Insights-UI Code Base Exploration and Setup
B. | InProgress Items
Product merge - Tech investigation
| Φ | INS-1182 | Understand the insight installation | Understanding on current jenkins pipeline and deployment on dev environment
[Events] Event Center Merge
| Φ | INS-1220 | Setup and configuration of Logstash on dev machine | Working on the changes related to SNOW event in logstash
| Φ | INS-1221 | MockAPI (Snow) & RabbitMQ publishing layer implementation | Created mock api for publishing, working on the routing changes
| Φ | INS-1224 | Create Event Center Page Shell & Navigation | Investigating existing changes and using similar template to create new screens
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | NA

## 22 Sept - 26 Sept 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
[Events] Event Center Merge
| Φ | INS-1221 | MockAPI (Snow) & RabbitMQ publishing layer implementation
Product merge - Tech investigation
| Φ | INS-1229 | Required stable Insights env for Dev team.
B. | InProgress Items
Product merge - Tech investigation
| Φ | INS-1182 | Understand the insight installation | Working with dev team, with logstash related setup.
| Φ | INS-1234 | Analyse all the Jenkins/GitHub pipelines used by Insights | analysis of Jenkinsfile of Meridian build to deploy
[Events] Event Center Merge
| Φ | INS-1223 | DAL layer modification to support firestorm feature | Investigate and modify certain code to accomodate specifc firestorm changes which will be useful
| Φ | INS-1220 | Setup and configuration of Logstash on dev machine | working on changing the logstash pipeline config on dev machine and trying to trigger the flow and test
| Φ | INS-1224 | Create Event Center Page Shell & Navigation | working on changes, completed sidebar, nav menu, page header
| Φ | INS-1225 | Implement Events Graph (Left Panel) | work started on event graph
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 2nd October | Gandhi Jayanti
B. | Team Members Leaves
| Φ | 24th September, 3rd October 2025 | Jairam Gauns

## 29 Sept - 03 Oct 2025
Risk
Φ | NA
Highlights
Φ | NA
Project Summary Details
A. | Completed Items
[Events] Event Center Merge
| Φ | INS-1220 | Setup and configuration of Logstash on dev machine
| Φ | INS-1219 | Configuration and creation of RabbitMQ queues dev machine
Product merge - Tech investigation
| Φ | INS-1182 | Understand the insight installation
| Φ | INS-1234 | Analyse all the Jenkins/GitHub pipelines used by Insights
B. | InProgress Items
[Events] Event Center Merge
| Φ | INS-1223 | DAL layer modification to support firestorm feature | Changes for flattening the view details completed. Working on list API under subtask INS-1235
| Φ | INS-1235 | API for Event List on Event Center | Implemented the API, checking for exclude list support from BT
| Φ | INS-1222 | Implementation Logstash processing mock API (snow) | Completed device enrichment, working on customer enrichment.
| Φ | INS-1224 | Create Event Center Page Shell & Navigation | Working on integrating the graph component with ECharts and mockdata
| Φ | INS-1225 | Implement Events Graph (Left Panel) | Event graph completed, working on implement the right panel with the events table
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 2nd October | Gandhi Jayanti
B. | Team Members Leaves
| Φ | 3rd October 2025 | Jairam Gauns
| Φ | 6th October 2025 | Sonal Yewale
| Φ | 6th October 2025 | Smita Chougule

## 06 Oct - 10 Oct 2025
Risk
Φ | NA
Highlights
Φ | We had to revert deployment on DEV VMs, as the current Jenkins deployment did not meet the branching strategy we created and team had to understand the Jenkins and go for a round about solution. Team is currently experimenting the deployment on a isolated QA system so that it does not block development activities.
Project Summary Details
A. | Completed Items
[Events] Event Center Merge
| Φ | INS-1223 | DAL layer modification to support firestorm feature
| Φ | INS-1222 | Implementation Logstash processing mock API (snow)
B. | InProgress Items
[Events] Event Center Merge
| Φ | INS-1235 | API for Event List on Event Center | Implemented and tested locally, working with UI team for integration
| Φ | INS-1237 | Define Event archive flow | Started with analysis of the flow in BT
| Φ | INS-1224 | Create Event Center Page Shell & Navigation | Changes completed, once API integration of INS-1225, INS-1244 is completed, PR will be raised
| Φ | INS-1225 | Implement Events Graph (Left Panel) | Event graph completed, working with API integration
| Φ | INS-1244 | Events-Screen[UI] : Implement Events List Table (Right Panel) | Reuse listing component completed, working with API integration
[PI4-2025] Tech debt
| Φ | INS-1256 | Run Test Deployment Pipelines on QA51 | Experimenting the deployment for specific UI and backend builds through Jenkins as the current build process is failing
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 20th October | Diwali Festival
B. | Team Members Leaves
| Φ | 21st, 22nd, 23rd, 24th October 2025 | Sonal Yewale
| Φ | 21st, 22nd, 23rd, 24th October 2025 | Saurabha Patane
| Φ | 21st, 22nd, 23rd, 24th October 2025 | Smita Chougule
| Φ | 21st, 23rd, 24th October 2025 | Payal Saindane
| Φ | 21st, 22nd October 2025 | Jairam Gauns
| Φ | 21st, 22nd October 2025 | Shilratna Somkuwar
| Φ | 22nd, 23rd October 2025 | Nikhil Naik

## 13 Oct - 17 Oct 2025
Risk
Φ | NA
Highlights
Φ | Had a sucessful demo with John, where we showed the Event Center Dashboard features with UI and backend integration Deployment on DEV VMs(kanchev) paused over QAWolf environment setup Team is working on setting up AWS environment for QAWolf, manual deployment completed, data population pending
Project Summary Details
A. | Completed Items
[Events] Event Center Merge
| Φ | INS-1235 | API for Event List on Event Center
| Φ | INS-1255 | Analysis of existing archive flow in firestorm
B. | InProgress Items
[Events] Event Center Merge
| Φ | INS-1237 | Define Event archive flow | Completed INS-1255, working on task INS-1257 under this story
| Φ | INS-1257 | Implement scheduled job to move cleared events to archive index | Working on the schedular changes to implement archival flow
| Φ | INS-1224 | Create Event Center Page Shell & Navigation | Draft PR raised, refactoring to be done after a merge from other team member changes
| Φ | INS-1225 | Implement Events Graph (Left Panel) | Draft PR raised, refactoring to be done after a merge from other team member changes
| Φ | INS-1244 | Events-Screen[UI] : Implement Events List Table (Right Panel) | Draft PR raised, refactoring to be done after a merge from other team member changes
| Φ | INS-1261 | API for Events Timeline | Started with analysis of the flow in BT
[PI4-2025] Tech debt
| Φ | INS-1256 | Run Test Deployment Pipelines on QA51 | On hold in favour on task INS-1242
| Φ | INS-1242 | Create a test environment | Completed the manual deployment, working on setup of data.
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | 20th, 21st October | Diwali Festival
B. | Team Members Leaves
| Φ | 22nd, 23rd, 24th October 2025 | Sonal Yewale
| Φ | 22nd, 23rd, 24th October 2025 | Saurabha Patane
| Φ | 22nd, 23rd, 24th October 2025 | Smita Chougule
| Φ | 23rd, 24th October 2025 | Payal Saindane
| Φ | 22nd, 23rd, 24th October 2025 | Jairam Gauns
| Φ | 22nd October 2025 | Shilratna Somkuwar
| Φ | 22nd, 23rd October 2025 | Nikhil Naik

## 20 Oct - 24 Oct 2025
Risk
Φ | NA
Highlights
Φ | Deployment on DEV VMs(kanchev) paused over QAWolf environment setup Setup on AWS environment for QAWolf, manual deployment completed, mock data population completed. Observed an issue which team is working on.
Project Summary Details
A. | Completed Items
[Events] Event Center Merge
| Φ | INS-1261 | API for Events Timeline
B. | InProgress Items
[Events] Event Center Merge
| Φ | INS-1237 | Define Event archive flow | Completed INS-1255, working on task INS-1257 under this story
| Φ | INS-1257 | Implement scheduled job to move cleared events to archive index | Working on the schedular changes to implement archival flow
| Φ | INS-1224 | Create Event Center Page Shell & Navigation | Draft PR raised, refactoring to be done after a merge from other team member changes
| Φ | INS-1225 | Implement Events Graph (Left Panel) | Draft PR raised, refactoring to be done after a merge from other team member changes
| Φ | INS-1244 | Events-Screen[UI] : Implement Events List Table (Right Panel) | Draft PR raised, refactoring to be done after a merge from other team member changes
[PI4-2025] Tech debt
| Φ | INS-1256 | Run Test Deployment Pipelines on QA51 | On hold in favour on task INS-1242
| Φ | INS-1242 | Create a test environment | Completed the manual deployment, working on setup of data.
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | NA

## 27 Oct - 31 Oct 2025
Risk
Φ | NA
Highlights
Φ | Deployment on DEV VMs(kanchev) paused over QAWolf environment setup Setup on AWS environment for QAWolf, manual deployment completed, resolved issues on services andadded data through file mode option of insight. Working on mockon APIs of the screens identified
Project Summary Details
A. | Completed Items
| Φ | NA
B. | InProgress Items
Adopt Mackoon APIs
| Φ | INS-1251 | Mock some of the Inventory APIs | Analysis started on this ticket
| Φ | INS-1249 | Add Mackoon to the cloud env | Setup is completed, once INS-1251 is even partially completed we can test and mark as complete
[Events] Event Center Merge
| Φ | INS-1237 | Define Event archive flow | Completed INS-1255, working on task INS-1257 under this story
| Φ | INS-1257 | Implement scheduled job to move cleared events to archive index | Working on listing API to follow OpenAPI specs
| Φ | INS-1224 | Create Event Center Page Shell & Navigation | Draft PR raised, refactoring to be done after a merge from other team member changes
| Φ | INS-1225 | Implement Events Graph (Left Panel) | Draft PR raised, refactoring to be done after a merge from other team member changes
| Φ | INS-1244 | Events-Screen[UI] : Implement Events List Table (Right Panel) | Draft PR raised, refactoring to be done after a merge from other team member changes
[PI4-2025] Tech debt
| Φ | INS-1242 | Create a test environment | Completed the manual deployment, couple of services related issues were resolved.
C. | Blocked Items
[PI4-2025] Tech debt
| Φ | INS-1256 | Run Test Deployment Pipelines on QA51 | On hold in favour on task INS-1242, INS-1249
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 27th October 2025 | Shilratna Somkuwar

## 03 Nov - 07 Nov 2025
Risk
Φ | NA
Highlights
Φ | Deployment on DEV VMs(kanchev) paused over QAWolf environment setup Setup on AWS is in progress for a new instance for QAWolf team as the previous instance setup was corrupted.
Project Summary Details
A. | Completed Items
Adopt Mackoon APIs
| Φ | INS-1249 | Add Mackoon to the cloud env
[Events] Event Center Merge
| Φ | INS-1224 | Create Event Center Page Shell & Navigation
| Φ | INS-1225 | Implement Events Graph (Left Panel)
| Φ | INS-1244 | Events-Screen[UI] : Implement Events List Table (Right Panel)
| Φ | INS-1279 | [Dropdown] Incorrect name of columns
[PI4-2025] Tech debt
| Φ | INS-1242 | Create a test environment
| Φ | INS-1256 | Run Test Deployment Pipelines on QA51
B. | InProgress Items
Adopt Mackoon APIs
| Φ | INS-1251 | Mock some of the Inventory APIs | Api development is in progress completed 3 APIs
| Φ | INS-1250 | Update the UI to use the Mackoon APIs for some cases | Team discussion on strategy to switch between mockoon and actual APIs
[Events] Event Center Merge
| Φ | INS-1237 | Define Event archive flow | Working on task INS-1257 under this story
| Φ | INS-1257 | Implement scheduled job to move cleared events to archive index | Completed search API working on aggregation API
| Φ | INS-1279 | [Dropdown] Incorrect name of columns | Bugfix is in progress
[PI4-2025] Tech debt
| Φ | INS-1271 | Automate Rabbitmq and Logstash configuration changes for Installer | In progress , completed consistent hash plugin changes
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 3rd, 4th November 2025 | Shilratna Somkuwar
| Φ | 6th November | Jairam Gauns

## 10 Nov - 14 Nov 2025
Risk
Φ | NA
Highlights
Φ | Deployment on DEV VMs(kanchev) paused over QAWolf environment setup Setup on AWS is in progress for a new instance for QAWolf team as the previous instance setup was corrupted.
Project Summary Details
A. | Completed Items
Adopt Mackoon APIs
| Φ | INS-1249 | Add Mackoon to the cloud env
[Events] Event Center Merge
| Φ | INS-1224 | Create Event Center Page Shell & Navigation
| Φ | INS-1225 | Implement Events Graph (Left Panel)
| Φ | INS-1244 | Events-Screen[UI] : Implement Events List Table (Right Panel)
| Φ | INS-1279 | [Dropdown] Incorrect name of columns
[PI4-2025] Tech debt
| Φ | INS-1242 | Create a test environment
| Φ | INS-1256 | Run Test Deployment Pipelines on QA51
B. | InProgress Items
Adopt Mackoon APIs
| Φ | INS-1251 | Mock some of the Inventory APIs | Api development is in progress completed 3 APIs
| Φ | INS-1250 | Update the UI to use the Mackoon APIs for some cases | Team discussion on strategy to switch between mockoon and actual APIs
[Events] Event Center Merge
| Φ | INS-1237 | Define Event archive flow | Working on task INS-1257 under this story
| Φ | INS-1257 | Implement scheduled job to move cleared events to archive index | Completed search API working on aggregation API
| Φ | INS-1279 | [Dropdown] Incorrect name of columns | Bugfix is in progress
[PI4-2025] Tech debt
| Φ | INS-1271 | Automate Rabbitmq and Logstash configuration changes for Installer | In progress , completed consistent hash plugin changes
C. | Blocked Items
| Φ | NA
Leaves / Company Holiday
A. | Company Holidays
| Φ | NA
B. | Team Members Leaves
| Φ | 12th, 13th November 2025 | Payal Saindane